## Dashboard
OCM IMPLEMENTATION DASHBOARD |  |  |  | INSTRUCTIONS
IMPLEMENTATION PROGRESS |  |  |  | PURPOSE
Phase | Total Activities | Completed | % Complete | Auto-populated dashboard showing
Foundation |  |  |  | OCM implementation status across
Pilot |  |  |  | all assessment areas.
Expansion
Optimization |  |  |  | DATA SOURCES
- Implementation Roadmap progress
ADKAR ASSESSMENT SUMMARY |  |  |  | - ADKAR scores from assessment
Element | Avg Score | Target | Gap | - Stakeholder risk calculations
Awareness |  | 4 |  | - KPI tracking values
Desire |  | 4 |  | - CSF and Maturity scores
Knowledge |  | 4
Ability |  | 4 |  | RISK INDICATORS
Reinforcement |  | 4 |  | High Risk: Score > 70
Medium Risk: Score 31-70
STAKEHOLDER RISK SUMMARY |  |  |  | Low Risk: Score <= 30
Metric | Value
Total Stakeholders |  |  |  | REFRESH
High Risk Count |  |  |  | All values auto-update when
Medium Risk Count |  |  |  | source sheets are modified.
Low Risk Count
Avg Adjusted Risk
Leadership Cascade Factor
Avg Depth Penalty
KPI SUMMARY
KPI | Current | Target | Status
Awareness Level
Adoption Rate
Proficiency Level
Resistance Level
Sponsor Engagement
Sustainment Rate
CRITICAL SUCCESS FACTORS
CSF | Score | Status
Overall CSF Score
MATURITY ASSESSMENT
Overall Maturity Score
Maturity Level

## Implementation Roadmap
INSTRUCTIONS
Activity | Phase | Owner | Status | Start Date | End Date | Notes
Secure executive sponsorship | Foundation | Sarah Chen | Complete | 2024-01-15 | 2024-01-22 | CEO fully committed | PURPOSE
Assess current OCM maturity | Foundation | Chris Lee | Complete | 2024-01-23 | 2024-02-05 | Level 2 - Emerging | Track implementation activities
Define OCM vision and objectives | Foundation | Michael Torres | Complete | 2024-02-06 | 2024-02-15 | Vision approved by steering committee | across 4 OCM capability phases.
Select OCM methodology | Foundation | Chris Lee | Complete | 2024-02-16 | 2024-02-28 | Prosci ADKAR selected
Identify pilot projects | Foundation | Jennifer Walsh | Complete | 2024-03-01 | 2024-03-10 | 3 pilots identified | PHASES
Build business case | Foundation | Lisa Johnson | Complete | 2024-03-11 | 2024-03-20 | ROI case approved | Foundation (Months 1-3)
Apply methodology to pilots | Pilot | David Kim | In Progress | 2024-03-21 |  | Pilot 1 underway | Pilot (Months 3-9)
Train pilot OCM leads | Pilot | Chris Lee | Complete | 2024-03-25 | 2024-04-05 | 8 leads certified | Expansion (Months 9-18)
Execute pilot change activities | Pilot | Amanda Foster | In Progress | 2024-04-01 |  | Week 6 of 12 | Optimization (Months 18+)
Capture lessons learned | Pilot | Emily Brown | Not Started
Demonstrate pilot value | Pilot | Michael Torres | Not Started |  |  |  | HOW TO USE
Refine methodology | Pilot | Chris Lee | Not Started |  |  |  | 1. Assign owners to activities
Expand OCM coverage | Expansion |  | Not Started |  |  |  | 2. Update status as work progresses
Formalize policies and standards | Expansion |  | Not Started |  |  |  | 3. Add start/end dates
Integrate with project management | Expansion |  | Not Started |  |  |  | 4. Add new activities as needed
Build change agent network | Expansion |  | Not Started
Develop manager orientation | Expansion |  | Not Started |  |  |  | STATUS VALUES
Establish governance | Expansion |  | Not Started |  |  |  | Not Started - Planned
Implement data-driven improvement | Optimization |  | Not Started |  |  |  | In Progress - Underway
Build change-ready culture | Optimization |  | Not Started |  |  |  | Complete - Done
Integrate with leadership development | Optimization |  | Not Started |  |  |  | On Hold - Paused
Establish continuous improvement | Optimization |  | Not Started
Plan practitioner succession | Optimization |  | Not Started
Benchmark against industry | Optimization |  | Not Started
Contribute to OCM body of knowledge | Optimization |  | Not Started

## ADKAR Assessment
INSTRUCTIONS
Stakeholder/Group | Awareness | Desire | Knowledge | Ability | Reinforcement | Avg Score | Barrier Point
Executive Team | 5 | 5 | 4 | 4 | 3 |  |  | PURPOSE
Senior Leadership | 5 | 4 | 4 | 3 | 3 |  |  | Assess stakeholder readiness
Middle Managers | 4 | 3 | 3 | 2 | 2 |  |  | using the ADKAR model.
IT Department | 5 | 4 | 4 | 4 | 3
HR/Training Team | 5 | 5 | 4 | 4 | 4 |  |  | ADKAR ELEMENTS
Operations - Team A | 3 | 2 | 2 | 1 | 1 |  |  | A - Awareness of need
Operations - Team B | 4 | 3 | 2 | 2 | 1 |  |  | D - Desire to participate
Finance Team | 4 | 3 | 3 | 2 | 2 |  |  | K - Knowledge of how
Admin Staff | 3 | 2 | 2 | 1 | 1 |  |  | A - Ability to implement
R - Reinforcement to sustain
SCORING SCALE
1 = No evidence
2 = Limited evidence
3 = Some evidence
4 = Strong evidence
5 = Full demonstration
BARRIER POINT
Auto-identifies the lowest
scoring element - focus
interventions here first.
TIP
Address elements sequentially.
Cannot build Desire without
first establishing Awareness.

## Stakeholder Analysis
[15 empty] | ROLE TEMPLATES |  |  |  |  | Cascade Factor: | STATE SCALE |  | INSTRUCTIONS
[15 empty] | Role | Power | Interest | Key Messages | Hierarchy | (Global) | State | Value
Name | Role Template | Department | Power | Interest | Current State | Desired State | Headcount | Time to Commit (wks) | Key Messages | Strategy | Base Risk | Cascade Factor | Depth Penalty | Adjusted Risk | Executive Sponsor | High | High | Strategic alignment, ROI, timeline, organizational impact | 1 |  | Unaware | 1 | PURPOSE
Sarah Chen | Executive Sponsor | Executive |  |  | Committed | Advocating | 1 | 1 | [6 empty] | Senior Leadership | High | Medium | Business case, resource needs, risks, department goals | 2 |  | Aware | 2 | Analyze stakeholders with
Michael Torres | Senior Leadership | Operations |  |  | Buy-in | Committed | 5 | 2 | [6 empty] | Middle Manager | Medium | High | Team impacts, timeline, support needed, performance metrics | 3 |  | Understanding | 3 | risk that cascades down
Jennifer Walsh | Senior Leadership | IT |  |  | Committed | Advocating | 4 | 2 | [6 empty] | Front-line Supervisor | Medium | High | Day-to-day impacts, team concerns, training needs | 4 |  | Buy-in | 4 | the organizational hierarchy.
David Kim | Middle Manager | Operations |  |  | Understanding | Committed | 12 | 4 | [6 empty] | End User (Heavy Impact) | Low | High | What changes, when, training, support available | 5 |  | Committed | 5
Lisa Johnson | Middle Manager | Finance |  |  | Aware | Buy-in | 8 | 5 | [6 empty] | End User (Light Impact) | Low | Medium | High-level overview, minimal disruption expected | 5 |  | Advocating | 6 | NEW COLUMNS
Robert Martinez | Middle Manager | HR |  |  | Buy-in | Committed | 6 | 3 | [6 empty] | IT Support Staff | Medium | High | Technical details, support requirements, timeline | 4 |  |  |  | Headcount: # of people in group
Amanda Foster | Front-line Supervisor | Operations |  |  | Aware | Buy-in | 45 | 6 | [6 empty] | HR/Training Team | Medium | High | Training needs, communication support, change impacts | 4 |  | DEPTH PENALTY |  | Time to Commit: est. weeks
James Wilson | Front-line Supervisor | Operations |  |  | Understanding | Committed | 38 | 5 | [6 empty] | Finance/Procurement | Medium | Medium | Budget, ROI, procurement timeline, cost controls | 3 |  | 'The body falters' effect: |  | Depth Penalty: body falters factor
Emily Brown | IT Support Staff | IT |  |  | Buy-in | Committed | 15 | 3 | [6 empty] | External Partner | Low | Medium | Integration points, timeline, support available | 5 |  | Level 1-2: No penalty (1.0)
Chris Lee | HR/Training Team | HR |  |  | Committed | Advocating | 8 | 2 | [6 empty] | Union Representative | Medium | High | Employee impacts, negotiation points, compliance | 3 |  | Level 3: +10% risk (1.1) |  | CASCADE LOGIC
Operations Team A | End User (Heavy Impact) | Operations |  |  | Unaware | Buy-in | 150 | 8 | [6 empty] | Customer | Low | Medium | Service improvements, transition period, support | 5 |  | Level 4: +20% risk (1.2) |  | Leadership aligned = -30-50%
Operations Team B | End User (Heavy Impact) | Operations |  |  | Aware | Committed | 120 | 7 | [12 empty] | Level 5: +30% risk (1.3) |  | But distance adds risk back:
Admin Staff | End User (Light Impact) | Admin |  |  | Unaware | Understanding | 45 | 6 | [14 empty] | Level 3: +10%
Finance Team | End User (Light Impact) | Finance |  |  | Aware | Buy-in | 25 | 5 | [12 empty] | Headcount amplifier: |  | Level 4: +20%
External Vendor | External Partner | External |  |  | Understanding | Buy-in | 10 | 4 | [12 empty] | >100 people: +10% |  | Level 5: +30%
>500 people: +20%
[21 empty] | >1000 people: +30% |  | HEADCOUNT AMPLIFIER
More people = more dilution
>100 people: +10% risk
>500 people: +20% risk
>1000 people: +30% risk
THE BODY FALTERS
Even with willing leadership,
message dilutes as it travels
down through layers.
Adjusted Risk = Base Risk
x Cascade Factor
x Depth Penalty

## Org Structure
ORGANIZATIONAL STRUCTURE & CASCADE IMPACT | [12 empty] | INSTRUCTIONS
Model how leadership strength/weakness cascades through reporting relationships
[11 empty] | STATE VALUES |  | PURPOSE
ID | Name | Role | Reports To (ID) | Direct Reports | Total Under | Current State | Leader State | Cascade Modifier | Effective State | Impact Score | State | Value | Model organizational hierarchy
L1 | Sarah Chen | Executive Sponsor |  | 2 | 492 | Committed | N/A (Top) |  |  |  | Unaware | 1 | and how leader strength/weakness
L2-1 | Michael Torres | VP Operations | L1 | 3 | 350 | Buy-in |  |  |  |  | Aware | 2 | cascades to their reports.
L2-2 | Jennifer Walsh | VP IT | L1 | 2 | 140 | Committed |  |  |  |  | Understanding | 3
L3-1 | David Kim | Ops Director | L2-1 | 4 | 200 | Understanding |  |  |  |  | Buy-in | 4 | THE MLM EFFECT
L3-2 | Lisa Johnson | Finance Director | L2-1 | 2 | 80 | Aware |  |  |  |  | Committed | 5 | Like MLM - your upline affects you:
L3-3 | Robert Martinez | HR Director | L2-1 | 2 | 65 | Buy-in |  |  |  |  | Advocating | 6
L3-4 | Emily Brown | IT Director | L2-2 | 3 | 85 | Committed | [6 empty] | Strong leader (Committed+):
L3-5 | Chris Lee | Training Manager | L2-2 | 1 | 50 | Advocating |  |  |  |  | CASCADE MODIFIERS |  | → 1.2x boost to your team
L4-1 | Amanda Foster | Ops Manager A | L3-1 | 2 | 80 | Aware |  |  |  |  | Leader State | Modifier
L4-2 | James Wilson | Ops Manager B | L3-1 | 2 | 70 | Understanding |  |  |  |  | Advocating/Committed | 1.2x (Boost) | Weak leader (Aware/Unaware):
L4-3 | Tom Harris | Ops Manager C | L3-1 | 1 | 30 | Buy-in |  |  |  |  | Buy-in | 1.0x (Neutral) | → 0.5-0.7x drag on your team
L4-4 | Nancy Clark | Ops Manager D | L3-1 | 1 | 15 | Unaware |  |  |  |  | Understanding | 0.85x (Drag)
L4-5 | Finance Manager | Finance Mgr | L3-2 | 1 | 35 | Aware |  |  |  |  | Aware | 0.7x (Weak) | Great middle manager can
L4-6 | Procurement Lead | Procurement | L3-2 | 0 | 40 | Understanding |  |  |  |  | Unaware | 0.5x (Failing) | BUFFER their team from a
L4-7 | HR Manager | HR Manager | L3-3 | 1 | 30 | Buy-in | [6 empty] | weak leader above them.
L4-8 | Training Lead | Training Lead | L3-3 | 0 | 30 | Committed
L4-9 | IT Support Lead | IT Support Mgr | L3-4 | 2 | 50 | Committed | [6 empty] | KEY COLUMNS
L4-10 | Dev Team Lead | Dev Manager | L3-4 | 1 | 20 | Buy-in | [6 empty] | Reports To: Parent's ID
L4-11 | Infra Lead | Infra Manager | L3-4 | 0 | 10 | Understanding | [6 empty] | Total Under: All subordinates
L5-1 | Team A Supervisor | Supervisor | L4-1 | 0 | 40 | Unaware | [6 empty] | Leader State: Your boss's state
L5-2 | Team B Supervisor | Supervisor | L4-1 | 0 | 35 | Aware | [6 empty] | Cascade Modifier: Boost/drag
L5-3 | Team C Supervisor | Supervisor | L4-2 | 0 | 35 | Understanding | [6 empty] | Effective State: Your adjusted state
L5-4 | Team D Supervisor | Supervisor | L4-2 | 0 | 30 | Aware | [6 empty] | Impact Score: Risk contribution
HOW TO USE
CASCADE IMPACT SUMMARY |  |  | HIERARCHY VISUALIZATION | [9 empty] | 1. Map your org hierarchy (IDs)
Total Organization Size |  |  | L1 (CEO) | [9 empty] | 2. Enter current states
Avg Effective State |  |  | ├── L2-1 (VP Ops) | [9 empty] | 3. Review cascade modifiers
Total Impact Score |  |  | │ ├── L3-1 (Ops Dir) ← WEAK | [9 empty] | 4. Identify weak links
High Risk Leaders (Impact>5) |  |  | │ │ ├── L4-1, L4-2, L4-3, L4-4 | [9 empty] | 5. Target interventions
Weak Links (Eff State<3) |  |  | │ │ └── L5-1, L5-2, L5-3, L5-4
Strong Multipliers (Mod>=1.2) |  |  | │ ├── L3-2 (Finance) | [9 empty] | TIP
Cascade Drag (Mod<1) |  |  | │ └── L3-3 (HR) | [9 empty] | Focus on leaders with high
|  |  | └── L2-2 (VP IT) ← STRONG | [9 empty] | Impact Score - they affect
|  |  | ├── L3-4 (IT Dir) | [9 empty] | the most people downstream.
└── L3-5 (Training) ← BUFFER

## Cascade Analysis
ORGANIZATIONAL CASCADE RISK ANALYSIS | [6 empty] | INSTRUCTIONS
HIERARCHY CASCADE MODEL | [6 empty] | PURPOSE
Level | Role Type | Typical Headcount | Time to Cascade (wks) | Cumulative Time | Dilution Factor | Cascade Health | Model how change cascades
1 | Executive Sponsor | [5 empty] | through organizational layers
2 | Senior Leadership | [5 empty] | and where it may falter.
3 | Middle Manager
4 | Front-line Supervisor | [5 empty] | KEY CONCEPTS
5 | End Users & Others | [5 empty] | Cascade Time: How long for
change to reach each level
THE BODY FALTERS ANALYSIS
Even when leadership is aligned, execution can falter in the middle layers. | [6 empty] | Dilution Factor: Message
degradation through layers
Factor | Current State | Impact | Mitigation Required
Middle Management Buy-in | Adequate | High - Key transmission layer | Dedicated manager engagement |  |  |  | Cascade Health: Effectiveness
Communication Channel Clarity | Weak | Medium - Message consistency | Cascade communication toolkit |  |  |  | of change transmission
Time Pressure on Managers | Weak | High - Competing priorities | Protected time for change activities
Training Capacity | Adequate | Medium - Skill transfer ability | Train-the-trainer program |  |  |  | THE BODY FALTERS
Change Fatigue | Strong | High - Resistance amplification | Phased rollout, quick wins |  |  |  | Leadership commitment alone
Local Context Adaptation | Adequate | Medium - One-size-fits-all risk | Flexible implementation guides |  |  |  | doesn't guarantee execution.
CASCADE TIMELINE PROJECTION | [6 empty] | Middle layers must:
Milestone | Week | Target Level | Expected Adoption % | Risk Factor |  |  | - Understand the why
Leadership Alignment |  | Levels 1-2 | 90% | Low |  |  | - Have capacity to act
Manager Engagement |  | Level 3 | 75% | Medium |  |  | - Be held accountable
Supervisor Cascade |  | Level 4 | 65% | Medium-High |  |  | - Receive ongoing support
Full Deployment |  | Level 5 | 55% | High
Stabilization (+4 wks) |  | All | 80% | Medium |  |  | USING THIS SHEET
Sustainment (+12 wks) |  | All | 85% | Low |  |  | 1. Review Stakeholder Analysis
2. Check hierarchy cascade times
SUMMARY METRICS | [6 empty] | 3. Assess body falters factors
Total Cascade Time (weeks) | [6 empty] | 4. Plan mitigation actions
Overall Dilution Factor | [6 empty] | 5. Set realistic timeline
Leadership Cascade Factor
Estimated Final Adoption | [6 empty] | TIP
Cascade Risk Rating | [6 empty] | If cascade time exceeds 16
weeks, consider parallel
tracks or direct skip-level
communication.

## Communication Plan
INSTRUCTIONS
Message | Audience | Channel | Sender | Timing | Status | Notes
Vision announcement | All staff | Town Hall | CEO | Week 1 |  |  | PURPOSE
Department briefing | Department heads | Meeting | Project Sponsor | Week 2 |  |  | Plan and track all change
Timeline communication | All affected | Email | Change Manager | Week 3 |  |  | communications across
Training announcement | End users | Intranet | HR/Training | Week 4 |  |  | stakeholder groups.
Go-live notification | All staff | Email + Intranet | IT Director | Go-live -1 week
KEY PRINCIPLES
- Right message, right time
- Appropriate channels
- Credible senders
- Two-way communication
CHANNELS
Email - Wide reach, formal
Meeting - Interactive, Q&A
Town Hall - Leadership visibility
Intranet - Reference info
Video - Engaging, repeatable
TIP
Managers are the preferred
channel for change details
affecting their teams.

## Training Plan
[10 empty] | ROLE TRAINING MATRIX |  |  |  | INSTRUCTIONS
[10 empty] | Role | Required Modules | Format | Priority
Training Module | Target Role | Format | Duration | Trainer | Target Headcount | Trained | Completion % | Date | Status | Executive Sponsor | Executive Briefing | Meeting | High | PURPOSE
Executive Briefing | Executive Sponsor | Meeting | 1 hour | Change Manager |  | 1 |  | 2024-03-15 | Complete | Senior Leadership | Leadership Overview, Change Sponsorship | Meeting | High | Role-based training plan
Leadership Overview | Senior Leadership | Meeting | 2 hours | Change Manager |  | 9 |  | 2024-03-20 | Complete | Middle Manager | Manager Toolkit, Cascade Communication, Coaching Skills | Workshop | High | auto-linked to Stakeholder
Change Sponsorship Workshop | Senior Leadership | Workshop | 4 hours | External Consultant |  | 7 |  | 2024-03-25 | Complete | Front-line Supervisor | Supervisor Guide, Team Communication, Basic System | Classroom | High | Analysis headcounts.
Manager Toolkit Training | Middle Manager | Workshop | 1 day | HR/Training Team |  | 18 |  | 2024-04-01 | In Progress | End User (Heavy Impact) | Full System Training, Process Changes, Hands-on Practice | Classroom | Critical
Cascade Communication Skills | Middle Manager | Classroom | 4 hours | HR/Training Team |  | 12 |  | 2024-04-05 | Scheduled | End User (Light Impact) | System Overview, Key Changes | eLearning | Medium | AUTO-CALCULATIONS
Supervisor Guide Training | Front-line Supervisor | Classroom | 4 hours | HR/Training Team |  | 25 |  | 2024-04-10 | Scheduled | IT Support Staff | Technical Deep-dive, Admin Functions, Troubleshooting | Hands-on | Critical | Target Headcount: Pulls from
Team Communication Workshop | Front-line Supervisor | Workshop | 2 hours | Change Manager |  | 0 |  | 2024-04-15 | Not Started | HR/Training Team | Train-the-Trainer, Full Curriculum, Facilitation | Workshop | Critical | Stakeholder Analysis by role
Full System Training | End User (Heavy Impact) | Classroom | 1 day | IT Training |  | 45 |  | 2024-04-20 | Not Started | Finance/Procurement | Process Changes, Reporting Updates | eLearning | Medium | Completion %: Trained/Target
System Overview (eLearning) | End User (Light Impact) | eLearning | 1 hour | Self-paced |  | 0 |  | 2024-04-15 | Not Started | External Partner | Integration Overview, API Changes | Video | Medium | Summary: Auto-totals
Technical Deep-dive | IT Support Staff | Hands-on | 2 days | Vendor |  | 15 |  | 2024-04-01 | Complete | Union Representative | Change Overview, Employee Impact Summary | Meeting | High
Train-the-Trainer | HR/Training Team | Workshop | 2 days | External Consultant |  | 8 |  | 2024-03-28 | Complete | Customer | Service Updates, New Features | Video | Low | HOW TO USE
1. Select Target Role (dropdown)
2. Headcount auto-populates
3. Enter Trained count
4. Update Status as needed
ROLE MATRIX
Reference table shows required
training modules and format
for each stakeholder role.
TIP
Add stakeholders first in
Stakeholder Analysis, then
training targets auto-update.
TRAINING SUMMARY
Total Target Headcount
Total Trained
Overall Completion %
Modules Complete
Modules In Progress
Modules Not Started

## Sponsorship Tracker
INSTRUCTIONS
Sponsor | Role | Activity | Due Date | Status | Effectiveness | Notes
| Executive Sponsor | Kick-off announcement |  |  |  |  | PURPOSE
| Executive Sponsor | Monthly steering committee |  |  |  |  | Track sponsor activities
| Executive Sponsor | Quarterly all-hands update |  |  |  |  | and effectiveness to ensure
| Project Sponsor | Weekly project reviews |  |  |  |  | visible leadership support.
| Project Sponsor | Stakeholder 1:1 meetings
| Department Head | Team briefings |  |  |  |  | SPONSOR ROLES
| Department Head | Resistance escalation review |  |  |  |  | Executive - Organization-wide
Project - Initiative leadership
Department - Local advocacy
KEY ACTIVITIES
- Communicate vision
- Build coalition
- Remove barriers
- Reinforce change
- Manage resistance
EFFECTIVENESS RATING
Highly Effective - Visible impact
Effective - Expected results
Needs Improvement - Limited
Ineffective - No visible support

## Resistance Log
INSTRUCTIONS
ID | Source | Type | Description | Root Cause | Mitigation | Owner | Status | Priority
R001 | [6 empty] | Open |  | PURPOSE
R002 | [6 empty] | Open |  | Track and manage resistance
R003 | [6 empty] | Open |  | to change systematically.
R004
R005 | [8 empty] | RESISTANCE TYPES
R006 | [8 empty] | Fear - Uncertainty about future
R007 | [8 empty] | Loss of Control - Autonomy concerns
R008 | [8 empty] | Workload - Capacity issues
R009 | [8 empty] | Skills Gap - Capability concerns
R010 | [8 empty] | Culture - Values conflict
R011 | [8 empty] | Past Experience - Previous failures
R012
R013 | [8 empty] | MANAGEMENT APPROACH
R014 | [8 empty] | 1. Identify early
R015 | [8 empty] | 2. Understand root cause
R016 | [8 empty] | 3. Plan mitigation
R017 | [8 empty] | 4. Monitor progress
R018 | [8 empty] | 5. Escalate if needed
R019
R020 | [8 empty] | TIP
R021 | [8 empty] | Resistance is often a symptom
R022 | [8 empty] | of insufficient Awareness,
R023 | [8 empty] | Desire, or Knowledge.
R024
R025
R026
R027
R028

## KPI Dashboard
INSTRUCTIONS
KPI | Definition | Current | Target | Status | Trend
Awareness Level | % of stakeholders aware of change | 78% | 100% |  | Improving | PURPOSE
Adoption Rate | % using new process/system correctly | 62% | 85% |  | Improving | Track 6 key OCM metrics
Proficiency Level | % meeting performance standards | 45% | 80% |  | Stable | against targets.
Resistance Level | % showing active resistance | 18% | ≤10% |  | Declining
Sponsor Engagement | Sponsor activity completion rate | 92% | 90% |  | Stable | KPI DEFINITIONS
Sustainment Rate | Sustained adoption after 90 days | N/A | 90% |  |  | Awareness - Survey/assessment
Adoption - System usage data
Proficiency - Quality metrics
Resistance - Log analysis
Sponsor - Activity tracking
Sustainment - 90-day review
MEASUREMENT FREQUENCY
Awareness: Weekly during rollout
Adoption: Weekly post go-live
Proficiency: Monthly
Resistance: Continuous
Sponsor: Per activity
Sustainment: 90 days post
TIP
Status auto-calculates
based on Current vs Target.

## Maturity Assessment
[6 empty] | MATURITY LEVELS |  | INSTRUCTIONS
[6 empty] | 1 - Ad-hoc | No formal OCM practices
Dimension | Description | Score | Evidence | Target | Gap | 2 - Emerging | Basic practices on some projects | PURPOSE
Leadership & Sponsorship | Executive commitment and visible support | 4 | CEO active sponsor, monthly steering | 5 |  | 3 - Defined | Standardized methodology in use | Assess organizational OCM
Methodology & Approach | Standardized OCM methodology application | 3 | ADKAR adopted, templates in use | 4 |  | 4 - Managed | Metrics-driven, consistent results | maturity across 8 dimensions.
Stakeholder Management | Systematic stakeholder analysis and engagement | 3 | Analysis complete, engagement ongoing | 4 |  | 5 - Optimized | Change-ready culture, continuous improvement
Communication | Planned, targeted change communications | 3 | Plan created, execution started | 4 |  |  |  | SCORING GUIDE
Training & Development | Role-based training and capability building | 2 | Initial training delivered | 4 |  |  |  | 1 = No evidence
Change Network | Established change agent infrastructure | 2 | 8 change agents identified | 3 |  |  |  | 2 = Limited/inconsistent
Resistance Management | Proactive identification and mitigation | 2 | Resistance log established | 4 |  |  |  | 3 = Defined process exists
Measurement & Sustainment | Metrics-driven improvement and reinforcement | 2 | KPIs defined, tracking started | 4 |  |  |  | 4 = Measured and managed
5 = Optimized, best practice
Overall Maturity Score
HOW TO USE
1. Score current state (1-5)
2. Set target state
3. Document evidence
4. Review gaps
5. Plan improvements
TIP
Conduct assessment annually
or after major initiatives.

## CSF Checklist
[5 empty] | SCORING GUIDE |  | INSTRUCTIONS
[5 empty] | 5 | Fully achieved, best practice
CSF # | Critical Success Factor | Score | Evidence | Actions Needed | 4 | Substantially achieved | PURPOSE
1 | Executive Sponsorship and Commitment | 5 | CEO is active sponsor, monthly updates | Maintain engagement cadence | 3 | Partially achieved | Evaluate 8 Critical Success
2 | Clear Vision and Case for Change | 4 | Vision documented, ROI case approved | Reinforce vision in communications | 2 | Limited achievement | Factors for OCM effectiveness.
3 | Stakeholder Engagement and Involvement | 3 | Analysis complete, engagement in progress | Increase middle mgmt engagement | 1 | Not achieved
4 | Effective Communication | 3 | Plan in place, execution underway | Add more two-way channels |  |  | CSF CATEGORIES
5 | Training and Capability Building | 2 | Initial curriculum designed | Develop role-based training paths |  |  | Leadership: CSF 1
6 | Change Agent Network | 2 | 8 agents identified and trained | Expand network to 20 agents |  |  | Foundation: CSF 2
7 | Resistance Management | 3 | Log established, active monitoring | Proactive outreach to resistors |  |  | People: CSF 3
8 | Measurement and Reinforcement | 2 | KPIs defined, tracking started | Establish reinforcement plan |  |  | Communication: CSF 4
Enablement: CSF 5
| Overall CSF Score | [5 empty] | Structure: CSF 6
Risk: CSF 7
Sustainability: CSF 8
HOW TO USE
1. Rate each CSF (1-5)
2. Document evidence
3. Identify actions needed
4. Review overall score
TIP
CSF 1 (Sponsorship) is the
strongest predictor of
change success.

## Risk Register
[9 empty] | RISK MATRIX | INSTRUCTIONS
ID | Risk Description | Category | Probability | Impact | Score | Mitigation | Owner | Status | Score = Probability x Impact
OCM-001 | Inadequate executive sponsorship | Leadership | [5 empty] | Open | 1-6: Low (Green) | PURPOSE
OCM-002 | Resistance from key stakeholder groups | People | [5 empty] | Open | 8-12: Medium (Yellow) | Track OCM-specific risks
OCM-003 | Insufficient training resources | Capability | [5 empty] | Open | 15-25: High (Red) | with probability and impact.
OCM-004 | Communication gaps | Communication | [5 empty] | Open
OCM-005 | Timeline compression | Schedule | [5 empty] | Open |  | CATEGORIES
OCM-006 | [7 empty] | Open |  | Leadership - Sponsorship risks
OCM-007 | [7 empty] | Open |  | People - Stakeholder resistance
OCM-008 | [7 empty] | Open |  | Capability - Skills/training
OCM-009 | [7 empty] | Open |  | Communication - Message gaps
OCM-010 | [7 empty] | Open |  | Schedule - Timeline risks
OCM-011 | [7 empty] | Open |  | Resource - Capacity issues
OCM-012 | [7 empty] | Open
OCM-013 | [7 empty] | Open |  | SCORING
OCM-014 | [7 empty] | Open |  | Probability: 1=Rare to 5=Certain
OCM-015 | [7 empty] | Open |  | Impact: 1=Minor to 5=Critical
OCM-016 | [7 empty] | Open |  | Score = P x I (auto-calculated)
OCM-017 | [7 empty] | Open
OCM-018 | [7 empty] | Open |  | MANAGEMENT
OCM-019 | [7 empty] | Open |  | High (15+): Escalate, urgent
OCM-020 | [7 empty] | Open |  | Medium (8-14): Monitor closely
Low (1-6): Track, review monthly

## Change Impact
[6 empty] | IMPACT SCALE |  | INSTRUCTIONS
Stakeholder Group | Process Impact | Technology Impact | People Impact | Overall Impact | Readiness Actions | 5 | Transformational - Fundamental change
Executive Team | [5 empty] | 4 | High - Significant change | PURPOSE
IT Department | [5 empty] | 3 | Moderate - Notable change | Assess change impact by
Operations | [5 empty] | 2 | Low - Minor adjustment | stakeholder group across
Sales | [5 empty] | 1 | Minimal - Little change | process, technology, people.
Customer Service
HR | [7 empty] | IMPACT DIMENSIONS
Finance | [7 empty] | Process - Workflow changes
Technology - System changes
People - Role/skill changes
HOW TO USE
1. List all affected groups
2. Rate each dimension (1-5)
3. Overall auto-calculates
4. Plan readiness actions
READINESS ACTIONS
High impact groups need:
- More communication
- Deeper training
- Closer support
- Earlier engagement