## Instructions
IT PORTFOLIO MANAGEMENT TEMPLATES
Based on the IT Portfolio Management Handbook
https://zettai-seigi.github.io/PortfolioManagementHandbook/
WORKSHEETS INCLUDED:
• Initiative Inventory
Master list of all portfolio initiatives with status tracking (500 row capacity)
• Business Case Template
Comprehensive investment proposal with executive summary, problem/opportunity, solution, and financials
• Alternatives Analysis
Structured comparison of solution options including Do Nothing baseline
• Scoring Worksheet
Multi-dimensional prioritization scoring (Business Value 40%, Risk 30%, Cost 30%)
• Cost Estimation
Detailed capital and operating cost breakdown with 3-year TCO
• Risk Assessment
Risk register with probability, impact, and mitigation strategies
• Benefits Tracking
Track projected vs realized benefits throughout the investment lifecycle
• Portfolio Dashboard
Executive dashboard with KPIs, composition, and at-risk initiatives
• Application Portfolio
Application inventory with TIME model classification (500 row capacity)
• Resource Capacity
Resource capacity planning by role with utilization tracking
• Implementation Timeline
Gantt-style project timeline with phases and milestones
• Reference Data
Scoring criteria, categories, and lookup values
COLOR CODING:
• Yellow cells: Input - Enter your data here
• Green cells: Calculated - Formulas calculate values automatically
• Blue (Dark): Headers - Section and column headers
• Blue (Light): Subheaders - Secondary headers
• Gray cells: Labels - Information and guidance
KEY FRAMEWORKS:
• Investment Categories (TGRC): Transform (15-25%), Grow (20-30%), Run (40-50%), Comply (10-15%)
• Application Categories (TIME): Tolerate, Invest, Migrate, Eliminate
• Priority Levels: P1-Critical, P2-High, P3-Medium, P4-Low
• Health Scores: 5=Excellent, 4=Good, 3=Concerning, 2=Poor, 1=Critical
• Scoring Formula: Priority = (Business Value × 40%) + ((5-Risk) × 30%) + ((5-Cost) × 30%)
USAGE TIPS:
1. Start with the Business Case Template when proposing new investments
2. Use the Scoring Worksheet to objectively prioritize initiatives
3. Track all active initiatives in the Initiative Inventory
4. Update the Portfolio Dashboard regularly for executive reporting
5. Monitor benefits realization using the Benefits Tracking sheet
6. Yellow cells often contain dropdown lists - click to see options
7. Green cells contain formulas - avoid manual entry
8. Customize Reference Data to match your organization's criteria

## Initiative Inventory
Initiative ID | Initiative Name | Business Sponsor | IT Sponsor | Category | Status | Priority | Health Score | Investment ($) | Annual Benefits | ROI (%) | Start Date | Target End | Actual End | Business Unit | % Complete | Key Risks/Issues
INI-001 | Customer Data Platform | Jane Smith | John Doe | Transform | In Execution | P1-Critical | 4-Good | 1500000 | 800000 | 53% | 2025-01-15 | 2025-09-30 |  | Sales | 45% | Integration complexity
INI-002 | ERP Upgrade | Bob Johnson | Sarah Lee | Run | In Planning | P2-High | 4-Good | 2000000 | 500000 | 25% | 2025-04-01 | 2025-12-31 |  | Finance | 10% | Resource availability
INI-003 | Mobile App Enhancement | Alice Brown | Mike Wilson | Grow | Proposed | P2-High | 5-Excellent | 500000 | 300000 | 60% |  |  |  | Marketing | 0%
INI-004 | Security Compliance | Risk Director | Security Lead | Comply | In Execution | P1-Critical | 3-Concerning | 800000 | 200000 | 25% | 2025-02-01 | 2025-06-30 |  | IT | 60% | Deadline pressure
INI-005
INI-006
INI-007
INI-008
INI-009
INI-010
INI-011
INI-012
INI-013
INI-014
INI-015
INI-016
INI-017
INI-018
INI-019
INI-020
INI-021
INI-022
INI-023
INI-024
INI-025
INI-026
INI-027
INI-028
INI-029
INI-030
INI-031
INI-032
INI-033
INI-034
INI-035
INI-036
INI-037
INI-038
INI-039
INI-040
INI-041
INI-042
INI-043
INI-044
INI-045
INI-046
INI-047
INI-048
INI-049
INI-050
INI-051
INI-052
INI-053
INI-054
INI-055
INI-056
INI-057
INI-058
INI-059
INI-060
INI-061
INI-062
INI-063
INI-064
INI-065
INI-066
INI-067
INI-068
INI-069
INI-070
INI-071
INI-072
INI-073
INI-074
INI-075
INI-076
INI-077
INI-078
INI-079
INI-080
INI-081
INI-082
INI-083
INI-084
INI-085
INI-086
INI-087
INI-088
INI-089
INI-090
INI-091
INI-092
INI-093
INI-094
INI-095
INI-096
INI-097
INI-098
INI-099
INI-100
INI-101
INI-102
INI-103
INI-104
INI-105
INI-106
INI-107
INI-108
INI-109
INI-110
INI-111
INI-112
INI-113
INI-114
INI-115
INI-116
INI-117
INI-118
INI-119
INI-120
INI-121
INI-122
INI-123
INI-124
INI-125
INI-126
INI-127
INI-128
INI-129
INI-130
INI-131
INI-132
INI-133
INI-134
INI-135
INI-136
INI-137
INI-138
INI-139
INI-140
INI-141
INI-142
INI-143
INI-144
INI-145
INI-146
INI-147
INI-148
INI-149
INI-150
INI-151
INI-152
INI-153
INI-154
INI-155
INI-156
INI-157
INI-158
INI-159
INI-160
INI-161
INI-162
INI-163
INI-164
INI-165
INI-166
INI-167
INI-168
INI-169
INI-170
INI-171
INI-172
INI-173
INI-174
INI-175
INI-176
INI-177
INI-178
INI-179
INI-180
INI-181
INI-182
INI-183
INI-184
INI-185
INI-186
INI-187
INI-188
INI-189
INI-190
INI-191
INI-192
INI-193
INI-194
INI-195
INI-196
INI-197
INI-198
INI-199
INI-200
INI-201
INI-202
INI-203
INI-204
INI-205
INI-206
INI-207
INI-208
INI-209
INI-210
INI-211
INI-212
INI-213
INI-214
INI-215
INI-216
INI-217
INI-218
INI-219
INI-220
INI-221
INI-222
INI-223
INI-224
INI-225
INI-226
INI-227
INI-228
INI-229
INI-230
INI-231
INI-232
INI-233
INI-234
INI-235
INI-236
INI-237
INI-238
INI-239
INI-240
INI-241
INI-242
INI-243
INI-244
INI-245
INI-246
INI-247
INI-248
INI-249
INI-250
INI-251
INI-252
INI-253
INI-254
INI-255
INI-256
INI-257
INI-258
INI-259
INI-260
INI-261
INI-262
INI-263
INI-264
INI-265
INI-266
INI-267
INI-268
INI-269
INI-270
INI-271
INI-272
INI-273
INI-274
INI-275
INI-276
INI-277
INI-278
INI-279
INI-280
INI-281
INI-282
INI-283
INI-284
INI-285
INI-286
INI-287
INI-288
INI-289
INI-290
INI-291
INI-292
INI-293
INI-294
INI-295
INI-296
INI-297
INI-298
INI-299
INI-300
INI-301
INI-302
INI-303
INI-304
INI-305
INI-306
INI-307
INI-308
INI-309
INI-310
INI-311
INI-312
INI-313
INI-314
INI-315
INI-316
INI-317
INI-318
INI-319
INI-320
INI-321
INI-322
INI-323
INI-324
INI-325
INI-326
INI-327
INI-328
INI-329
INI-330
INI-331
INI-332
INI-333
INI-334
INI-335
INI-336
INI-337
INI-338
INI-339
INI-340
INI-341
INI-342
INI-343
INI-344
INI-345
INI-346
INI-347
INI-348
INI-349
INI-350
INI-351
INI-352
INI-353
INI-354
INI-355
INI-356
INI-357
INI-358
INI-359
INI-360
INI-361
INI-362
INI-363
INI-364
INI-365
INI-366
INI-367
INI-368
INI-369
INI-370
INI-371
INI-372
INI-373
INI-374
INI-375
INI-376
INI-377
INI-378
INI-379
INI-380
INI-381
INI-382
INI-383
INI-384
INI-385
INI-386
INI-387
INI-388
INI-389
INI-390
INI-391
INI-392
INI-393
INI-394
INI-395
INI-396
INI-397
INI-398
INI-399
INI-400
INI-401
INI-402
INI-403
INI-404
INI-405
INI-406
INI-407
INI-408
INI-409
INI-410
INI-411
INI-412
INI-413
INI-414
INI-415
INI-416
INI-417
INI-418
INI-419
INI-420
INI-421
INI-422
INI-423
INI-424
INI-425
INI-426
INI-427
INI-428
INI-429
INI-430
INI-431
INI-432
INI-433
INI-434
INI-435
INI-436
INI-437
INI-438
INI-439
INI-440
INI-441
INI-442
INI-443
INI-444
INI-445
INI-446
INI-447
INI-448
INI-449
INI-450
INI-451
INI-452
INI-453
INI-454
INI-455
INI-456
INI-457
INI-458
INI-459
INI-460
INI-461
INI-462
INI-463
INI-464
INI-465
INI-466
INI-467
INI-468
INI-469
INI-470
INI-471
INI-472
INI-473
INI-474
INI-475
INI-476
INI-477
INI-478
INI-479
INI-480
INI-481
INI-482
INI-483
INI-484
INI-485
INI-486
INI-487
INI-488
INI-489
INI-490
INI-491
INI-492
INI-493
INI-494
INI-495
INI-496
INI-497
INI-498
INI-499

## Business Case Template
BUSINESS CASE TEMPLATE
1. EXECUTIVE SUMMARY
Initiative Name: |  | Initiative ID:
Business Sponsor: |  | IT Sponsor:
Submission Date: |  | Version:
Department: |  | Investment Category:
Financial Summary
Requested Investment: |  | Expected Annual Benefits:
ROI (3-Year): |  | Payback Period:
NPV: |  | IRR:
Strategic Alignment:
Recommendation:
2. BUSINESS PROBLEM/OPPORTUNITY
Business Problem:
Business Impact of Inaction:
Root Cause Analysis:
Opportunity Description:
Urgency/Timing Drivers:
3. PROPOSED SOLUTION
Solution Description:
In Scope:
Out of Scope:
Implementation Approach:
Key Technology Components:
Integration Points:
External Dependencies:
4. COST ESTIMATION
Capital Costs (One-Time)
Cost Category | Low | Expected | High | Notes
Hardware
Software Licenses
Implementation Services
Internal Project Costs
Data Migration
Testing
Training
Change Management
Contingency (15-20%)
TOTAL CAPITAL
Annual Operating Costs (Recurring)
Cost Category | Low | Expected | High | Notes
Support & Maintenance
Cloud/Infrastructure
License Renewals
Internal Support
Ongoing Training
Minor Enhancements
TOTAL OPERATING
5. BENEFITS
Benefit Description | Type | Year 1 | Year 2 | Year 3 | Owner
6. KEY RISKS
Risk Description | Category | Probability | Impact | Score | Mitigation
7. APPROVALS
Role | Name | Decision | Date | Comments
Business Sponsor
IT Sponsor
Finance Review
Architecture Review
Investment Board

## Alternatives Analysis
ALTERNATIVES ANALYSIS
Criteria | Option 1: Do Nothing | Option 2: [Name] | Option 3: [Name] | Option 4: [Name]
Description
Key Assumptions
Pros
Cons
Capital Cost ($)
Annual Operating Cost ($)
3-Year TCO ($)
Annual Benefits ($)
3-Year ROI (%)
Payback (months)
Technical Risk (L/M/H)
Delivery Risk (L/M/H)
Business Risk (L/M/H)
Time to Implement
Resource Requirements
Strategic Fit (1-5)
Recommended?
Recommendation Rationale

## Scoring Worksheet
INITIATIVE SCORING WORKSHEET
Initiative Name:
Initiative ID: |  | Scoring Date:
Scoring Committee:
BUSINESS VALUE ASSESSMENT (40% of Total)
Dimension | Weight | Score (0-5) | Weighted Score | Rationale
Strategic Alignment | 25%
Financial Impact | 25%
Customer Impact | 20%
Operational Impact | 15%
Competitive Impact | 15%
BUSINESS VALUE SCORE
RISK ASSESSMENT (30% of Total) - Higher = More Risk
Dimension | Weight | Score (0-5) | Weighted Score | Rationale
Technical Risk | 25%
Delivery Risk | 25%
Business Risk | 20%
Organizational Risk | 15%
External Risk | 15%
RISK SCORE
COST ASSESSMENT (30% of Total) - Higher = More Costly
Dimension | Weight | Score (0-5) | Weighted Score | Rationale
Capital Cost | 30%
Operating Cost | 25%
Resource Cost | 25%
Total Cost of Ownership | 20%
COST SCORE
PRIORITY CALCULATION
Business Value Score (40%):
Risk Score Inverted (5 - Risk):
Cost Score Inverted (5 - Cost):
FINAL PRIORITY SCORE:
PRIORITY CLASSIFICATION:
SCORING GUIDE
5 = Exceptional - Highest level of alignment/impact/risk
4 = High - Strong alignment, significant impact/risk
3 = Moderate - Adequate alignment, noticeable impact/risk
2 = Low - Limited alignment, minor impact/risk
1 = Minimal - Negligible alignment/impact/risk
0 = None - No alignment/impact/risk

## Cost Estimation
COST ESTIMATION WORKSHEET
Initiative Name:
CAPITAL COSTS (ONE-TIME)
Cost Category | Low Estimate | Expected | High Estimate | Assumptions/Notes
Hardware (servers, storage, network)
Software Licenses
Implementation Services (vendor)
Internal Project Team Costs
Data Migration
System Integration
Testing (QA, UAT, performance)
Training Development
Change Management
Project Management
Contingency (15-20%)
TOTAL CAPITAL COSTS
ANNUAL OPERATING COSTS (RECURRING)
Cost Category | Low Estimate | Expected | High Estimate | Assumptions/Notes
Support & Maintenance (18-22% of licenses)
Cloud/Infrastructure Hosting
License Renewals/SaaS Subscriptions
Internal Support Staff (FTE)
Help Desk Support
Ongoing Training
Minor Enhancements/Changes
Vendor Management
TOTAL ANNUAL OPERATING
TOTAL COST OF OWNERSHIP (3-YEAR)
Year 0 - Capital Investment:
Year 1 - Operating:
Year 2 - Operating:
Year 3 - Operating:
TOTAL 3-YEAR TCO:

## Risk Assessment
RISK ASSESSMENT REGISTER
Initiative Name:
RISK MATRIX: | Probability: 1=Rare, 2=Unlikely, 3=Possible, 4=Likely, 5=Almost Certain
Impact: 1=Negligible, 2=Minor, 3=Moderate, 4=Major, 5=Severe
Risk Score = Probability × Impact: 1-6=Low (Green), 7-14=Medium (Yellow), 15-25=High (Red)
ID | Category | Risk Description | Probability (1-5) | Impact (1-5) | Score | Mitigation Strategy | Owner | Status
R1
R2
R3
R4
R5
R6
R7
R8
R9
R10
R11
R12
R13
R14
R15
R16
R17
R18
R19
R20
RISK SUMMARY
Total Risks:
High Risks (15+):
Medium Risks (7-14):
Low Risks (1-6):
Average Risk Score:

## Benefits Tracking
BENEFITS REALIZATION TRACKING
BENEFITS REGISTER
Initiative | Benefit Description | Type | Planned Value | Realized Value | Variance | % Achieved | Status | Owner | Measurement
CRM Implementation | Reduced sales cycle time | Productivity | 200000 | 180000 |  |  | Tracking | Sales Director | CRM reports
CRM Implementation | Increased win rate | Revenue | 500000 | 450000 |  |  | Tracking | Sales Director | Sales metrics
ERP Upgrade | Reduced manual processing | Cost Savings | 150000 | 0 |  |  | Not Started | Finance Director | Process metrics
Security Project | Avoided breach costs | Risk Mitigation | 1000000 | 1000000 |  |  | Fully Realized | CISO | Security reports
BENEFITS SUMMARY
Total Planned Benefits:
Total Realized Benefits:
Overall Realization Rate:

## Portfolio Dashboard
IT PORTFOLIO DASHBOARD
Report Date: December 2025
KEY PORTFOLIO METRICS
Metric | Current | Target | Trend | Status
Portfolio Health Score | 4.2 | ≥4.0 | ↑ | On Target
On-Time Delivery Rate | 82% | ≥85% | → | At Risk
On-Budget Delivery Rate | 91% | ≥90% | ↑ | On Target
Benefits Realization Rate | 78% | ≥85% | ↓ | Below Target
Resource Utilization | 84% | 80-85% | → | On Target
Strategic Alignment | 85% | ≥80% | ↑ | On Target
PORTFOLIO COMPOSITION BY CATEGORY
Category | # Initiatives | Investment ($) | % of Total | Target % | Variance
Transform | 8 | 4500000 | 22% | 15-25% | On Target
Grow | 12 | 5200000 | 26% | 20-30% | On Target
Run | 25 | 8500000 | 42% | 40-50% | On Target
Comply | 5 | 2000000 | 10% | 10-15% | On Target
TOTAL | 50 | 20200000 | 100% | 100% | -
TOP 10 INITIATIVES
# | Initiative | Category | Investment | Status | Health | Target End | Issues
1 | Customer Data Platform | Transform | $1.5M | In Execution | 4-Good | Sep 2025 | Integration delays
2 | ERP Upgrade | Run | $2.0M | In Planning | 4-Good | Dec 2025 | Resource constraints
3 | Security Compliance | Comply | $0.8M | In Execution | 3-Concerning | Jun 2025 | Timeline pressure
4
5
6
7
8
9
10
AT-RISK INITIATIVES
Initiative | Issue | Impact | Mitigation | Owner | Due Date

## Application Portfolio
App ID | Application Name | Business Owner | IT Owner | Category | Lifecycle | Business Value | Technical Health | TIME Class | Annual Cost | Users | Vendor | Notes
APP-001 | Customer CRM | Sales Director | CRM Lead | Strategic | Mature | 5-Critical | 4-Good | Invest | 250000 | 500 | Salesforce | Core sales platform
APP-002 | HR System | HR Director | HR IT Lead | Core | Mature | 3-Medium | 3-Fair | Tolerate | 120000 | 200 | Workday
APP-003 | Legacy Billing | Finance Dir | Finance IT | Retire | Declining | 2-Low | 2-Poor | Migrate | 80000 | 50 | Custom | Replace by 2026
APP-004
APP-005
APP-006
APP-007
APP-008
APP-009
APP-010
APP-011
APP-012
APP-013
APP-014
APP-015
APP-016
APP-017
APP-018
APP-019
APP-020
APP-021
APP-022
APP-023
APP-024
APP-025
APP-026
APP-027
APP-028
APP-029
APP-030
APP-031
APP-032
APP-033
APP-034
APP-035
APP-036
APP-037
APP-038
APP-039
APP-040
APP-041
APP-042
APP-043
APP-044
APP-045
APP-046
APP-047
APP-048
APP-049
APP-050
APP-051
APP-052
APP-053
APP-054
APP-055
APP-056
APP-057
APP-058
APP-059
APP-060
APP-061
APP-062
APP-063
APP-064
APP-065
APP-066
APP-067
APP-068
APP-069
APP-070
APP-071
APP-072
APP-073
APP-074
APP-075
APP-076
APP-077
APP-078
APP-079
APP-080
APP-081
APP-082
APP-083
APP-084
APP-085
APP-086
APP-087
APP-088
APP-089
APP-090
APP-091
APP-092
APP-093
APP-094
APP-095
APP-096
APP-097
APP-098
APP-099
APP-100
APP-101
APP-102
APP-103
APP-104
APP-105
APP-106
APP-107
APP-108
APP-109
APP-110
APP-111
APP-112
APP-113
APP-114
APP-115
APP-116
APP-117
APP-118
APP-119
APP-120
APP-121
APP-122
APP-123
APP-124
APP-125
APP-126
APP-127
APP-128
APP-129
APP-130
APP-131
APP-132
APP-133
APP-134
APP-135
APP-136
APP-137
APP-138
APP-139
APP-140
APP-141
APP-142
APP-143
APP-144
APP-145
APP-146
APP-147
APP-148
APP-149
APP-150
APP-151
APP-152
APP-153
APP-154
APP-155
APP-156
APP-157
APP-158
APP-159
APP-160
APP-161
APP-162
APP-163
APP-164
APP-165
APP-166
APP-167
APP-168
APP-169
APP-170
APP-171
APP-172
APP-173
APP-174
APP-175
APP-176
APP-177
APP-178
APP-179
APP-180
APP-181
APP-182
APP-183
APP-184
APP-185
APP-186
APP-187
APP-188
APP-189
APP-190
APP-191
APP-192
APP-193
APP-194
APP-195
APP-196
APP-197
APP-198
APP-199
APP-200
APP-201
APP-202
APP-203
APP-204
APP-205
APP-206
APP-207
APP-208
APP-209
APP-210
APP-211
APP-212
APP-213
APP-214
APP-215
APP-216
APP-217
APP-218
APP-219
APP-220
APP-221
APP-222
APP-223
APP-224
APP-225
APP-226
APP-227
APP-228
APP-229
APP-230
APP-231
APP-232
APP-233
APP-234
APP-235
APP-236
APP-237
APP-238
APP-239
APP-240
APP-241
APP-242
APP-243
APP-244
APP-245
APP-246
APP-247
APP-248
APP-249
APP-250
APP-251
APP-252
APP-253
APP-254
APP-255
APP-256
APP-257
APP-258
APP-259
APP-260
APP-261
APP-262
APP-263
APP-264
APP-265
APP-266
APP-267
APP-268
APP-269
APP-270
APP-271
APP-272
APP-273
APP-274
APP-275
APP-276
APP-277
APP-278
APP-279
APP-280
APP-281
APP-282
APP-283
APP-284
APP-285
APP-286
APP-287
APP-288
APP-289
APP-290
APP-291
APP-292
APP-293
APP-294
APP-295
APP-296
APP-297
APP-298
APP-299
APP-300
APP-301
APP-302
APP-303
APP-304
APP-305
APP-306
APP-307
APP-308
APP-309
APP-310
APP-311
APP-312
APP-313
APP-314
APP-315
APP-316
APP-317
APP-318
APP-319
APP-320
APP-321
APP-322
APP-323
APP-324
APP-325
APP-326
APP-327
APP-328
APP-329
APP-330
APP-331
APP-332
APP-333
APP-334
APP-335
APP-336
APP-337
APP-338
APP-339
APP-340
APP-341
APP-342
APP-343
APP-344
APP-345
APP-346
APP-347
APP-348
APP-349
APP-350
APP-351
APP-352
APP-353
APP-354
APP-355
APP-356
APP-357
APP-358
APP-359
APP-360
APP-361
APP-362
APP-363
APP-364
APP-365
APP-366
APP-367
APP-368
APP-369
APP-370
APP-371
APP-372
APP-373
APP-374
APP-375
APP-376
APP-377
APP-378
APP-379
APP-380
APP-381
APP-382
APP-383
APP-384
APP-385
APP-386
APP-387
APP-388
APP-389
APP-390
APP-391
APP-392
APP-393
APP-394
APP-395
APP-396
APP-397
APP-398
APP-399
APP-400
APP-401
APP-402
APP-403
APP-404
APP-405
APP-406
APP-407
APP-408
APP-409
APP-410
APP-411
APP-412
APP-413
APP-414
APP-415
APP-416
APP-417
APP-418
APP-419
APP-420
APP-421
APP-422
APP-423
APP-424
APP-425
APP-426
APP-427
APP-428
APP-429
APP-430
APP-431
APP-432
APP-433
APP-434
APP-435
APP-436
APP-437
APP-438
APP-439
APP-440
APP-441
APP-442
APP-443
APP-444
APP-445
APP-446
APP-447
APP-448
APP-449
APP-450
APP-451
APP-452
APP-453
APP-454
APP-455
APP-456
APP-457
APP-458
APP-459
APP-460
APP-461
APP-462
APP-463
APP-464
APP-465
APP-466
APP-467
APP-468
APP-469
APP-470
APP-471
APP-472
APP-473
APP-474
APP-475
APP-476
APP-477
APP-478
APP-479
APP-480
APP-481
APP-482
APP-483
APP-484
APP-485
APP-486
APP-487
APP-488
APP-489
APP-490
APP-491
APP-492
APP-493
APP-494
APP-495
APP-496
APP-497
APP-498
APP-499

## Resource Capacity
RESOURCE CAPACITY PLANNING
CAPACITY SUMMARY BY ROLE
Role | Total FTE | Available | Allocated | Util % | Q1 | Q2 | Q3 | Q4 | Gap
Project Manager | 8 | 7.5 | 6.8 | 91% | 7 | 7.5 | 7 | 6.5
Business Analyst | 6 | 5.5 | 5 | 91% | 5.2 | 5.5 | 5 | 4.8
Solution Architect | 4 | 3.8 | 3.5 | 92% | 3.8 | 4 | 3.5 | 3
Developer - Java | 15 | 14 | 12.5 | 89% | 13 | 14 | 13 | 12
Developer - .NET | 10 | 9.5 | 8.8 | 93% | 9 | 9.5 | 9 | 8.5
QA Analyst | 8 | 7.5 | 7 | 93% | 7.5 | 8 | 7.5 | 7
DevOps Engineer | 5 | 4.8 | 4.5 | 94% | 4.8 | 5 | 4.8 | 4.5
DBA | 3 | 2.8 | 2.5 | 89% | 2.5 | 2.8 | 2.5 | 2.3
TOTAL

## Implementation Timeline
IMPLEMENTATION TIMELINE
Initiative Name:
Phase/Activity | Start | End | Days | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12
PHASE 1: PLANNING
Project Kickoff
Requirements Gathering
Detailed Design
Vendor Selection
Contract Negotiation
PHASE 2: BUILD
Environment Setup
Development/Configuration
Integration Development
Data Migration
PHASE 3: TEST
Unit Testing
System Integration Testing
User Acceptance Testing
Performance Testing
PHASE 4: DEPLOY
Training
Change Management
Go-Live
Hypercare
PHASE 5: CLOSE
Benefits Baseline
Project Closure
Lessons Learned
KEY MILESTONES
Milestone | Target Date | Actual Date | Status
Project Kickoff
Requirements Sign-off
Design Complete
Development Complete
UAT Sign-off
Go-Live
Project Closure

## Reference Data
REFERENCE DATA AND SCORING CRITERIA
INVESTMENT CATEGORIES (TGRC)
Category | Description | Target % | Examples
Transform | New capabilities, strategic innovation | 15-25% | Digital platforms, AI/ML, new business models
Grow | Expand existing capabilities | 20-30% | Feature enhancements, capacity expansion
Run | Maintain operations | 40-50% | Maintenance, upgrades, technical debt
Comply | Regulatory and security | 10-15% | Compliance, security, audit requirements
SCORING CRITERIA (0-5 SCALE)
Score | Label | Description
5 | Exceptional | Highest level - critical strategic alignment, transformative impact
4 | High | Strong alignment, significant impact, above average
3 | Moderate | Adequate alignment, noticeable impact, meets expectations
2 | Low | Limited alignment, minor impact, below expectations
1 | Minimal | Negligible alignment or impact
0 | None | No alignment, impact, or relevance
PRIORITY CLASSIFICATION
Priority | Score Range | Action | Funding
P1 - Critical | 4.0 - 5.0 | Fund immediately | Current cycle
P2 - High | 3.0 - 3.99 | Fund this cycle | Current cycle
P3 - Medium | 2.0 - 2.99 | Consider next cycle | Next cycle
P4 - Low | 0 - 1.99 | Defer or decline | Future/Never
APPLICATION TIME MODEL
Classification | Description | Action
Tolerate | Adequate but not ideal, low priority for change | Maintain, minimal investment
Invest | High value, strategic importance | Enhance, modernize, expand
Migrate | Needs replacement or major upgrade | Plan transition to new platform
Eliminate | Low value, high cost or risk | Retire, decommission
KEY PERFORMANCE INDICATORS (KPIs)
KPI | Target | Measurement
Portfolio Health Score | ≥4.0 (out of 5) | Average health score across active initiatives
On-Time Delivery | ≥85% | % of initiatives completing on schedule
On-Budget Delivery | ≥90% | % of initiatives completing within budget
Benefits Realization | ≥85% | % of projected benefits achieved
Resource Utilization | 80-85% | % of capacity allocated to portfolio work
Strategic Alignment | ≥80% | % of investment in strategic categories